## Sheet1
Activity ID | Activity Status | WBS Code | Activity Name | Start | Finish | Resources | Resource ID | Resource Name | Title | Predecessor | Successor | Relationship Type | Predecessor Activity Status | Successor Activity Status | Predecessor Project | Successor Project | Predecessor WBS | Successor WBS | Predecessor Activity Name | Successor Activity Name | Lag(d) | Predecessor Primary Resource | Successor Primary Resource | Expense Item | Budgeted Cost | Actual Cost | Remaining Cost | At Completion Cost | Activity ID_1 | Activity Status_2
A1000 | Completed | O and G.1 | Project Kickoff Meeting | 2025-02-03 08:00 | 2025-02-04 17:00 | Project Manager | MathisL | Lane Mathis, CIO |  | A1000 | A1010 | FS | Completed | Completed | O and G | O and G | O and G.1 (New WBS) | O and G.1 (New WBS) | Project Kickoff Meeting | Site Servay | 0 | R-11 | R-11 |  | 528000 | 528000 | 628000
A1010 | Completed | O and G.1 | Site Servay | 2025-02-05 08:00 | 2025-02-09 16:00 | Project Manager, Civil Engineer | AndersonG | Glen Anderson, VP Development |  | A1010 | A1020 | FS | Completed | Completed | O and G | O and G | O and G.1 (New WBS) | O and G.1 (New WBS) | Site Servay | Approval and permits | 0 | R-11 | R-11 |  | 48000 | 48000 | 58000
A1020 | Completed | O and G.1 | Approval and permits | 2025-02-10 08:00 | 2025-02-16 16:00 | Project Manager, Civil Engineer | VincentI | Ian Vincent |  | A1020 | A1030 | SS | Completed | In Progress | O and G | O and G | O and G.1 (New WBS) | O and G.2 (New WBS)-1 | Approval and permits | Pipeline rotune Finalization | 0 | R-11 | R-12 |  | 200000 | 200000 | 200000
A1030 | In Progress | O and G.2 | Pipeline rotune Finalization | 2025-02-17 08:00 | 2025-02-06 12:00 | Civil Engineer | CharlesM | Mandy Charles, VP IT Ops |  | A1030 | A1040 | SS | In Progress | In Progress | O and G | O and G | O and G.2 (New WBS)-1 | O and G.2 (New WBS)-1 | Pipeline rotune Finalization | Pipeline Engineering Design | 0 | R-12 | R-13 |  | 280000 | 280000 | 280000
A1040 | In Progress | O and G.2 | Pipeline Engineering Design | 2025-02-24 08:00 | 2025-02-13 17:00 | Mechinacal Engineer | ZhuS | Shannon Zhu |  | A1040 | A1050 | SS | In Progress | In Progress | O and G | O and G | O and G.2 (New WBS)-1 | O and G.2 (New WBS)-1 | Pipeline Engineering Design | Design Review | 0 | R-13 | R-11 |  | 544000 | 272000 | 544000
A1050 | In Progress | O and G.2 | Design Review | 2025-03-11 08:00 | 2025-02-15 12:00 | Project Manager, Mechinacal Engineer | LaffertyV | Vanessa Lafferty |  | A1050 | A1060 | SS | In Progress | Not Started | O and G | O and G | O and G.2 (New WBS)-1 | O and G.3 (New WBS)-2 | Design Review | Material Procurement | 0 | R-11 |  |  | 112000 | 56000 | 112000
A1060 | Not Started | O and G.3 | Material Procurement | 2025-02-14 08:00 | 2025-02-23 16:00 | Materials | BennettC | Carina Bennett |  | A1060 | A1070 | FS | Not Started | Not Started | O and G | O and G | O and G.3 (New WBS)-2 | O and G.3 (New WBS)-2 | Material Procurement | Equipment Procurement | 0 |  |  |  | 300000 | 150000 | 300000
A1070 | Not Started | O and G.3 | Equipment Procurement | 2025-02-24 08:00 | 2025-03-07 17:00 | Materials | PaxsonD | Dan Paxson |  | A1070 | A1080 | FS | Not Started | Not Started | O and G | O and G | O and G.3 (New WBS)-2 | O and G.3 (New WBS)-2 | Equipment Procurement | Vandor Inspections | 0 |  | R-11 |  | 132000 | 66000 | 132000
A1080 | Not Started | O and G.3 | Vandor Inspections | 2025-03-08 08:00 | 2025-03-12 17:00 | Project Manager | SinghD | Deepak Singh |  | A1080 | A1090 | FS | Not Started | Not Started | O and G | O and G | O and G.3 (New WBS)-2 | O and G.4 (New WBS)-3 | Vandor Inspections | Mobalization | 0 | R-11 | R-12 |  | 31800000 | 528000 | 32800000
A1090 | Not Started | O and G.4 | Mobalization | 2025-03-13 08:00 | 2025-03-17 17:00 | Civil Engineer | SharpeD | Dan Sharpe |  | A1090 | A1100 | SF | Not Started | Not Started | O and G | O and G | O and G.4 (New WBS)-3 | O and G.4 (New WBS)-3 | Mobalization | Trenching and Excavation | 0 | R-12 | R-12 |  | 14400000 | 48000 | 14800000
A1100 | Not Started | O and G.4 | Trenching and Excavation | 2025-03-18 08:00 | 2025-04-01 17:00 | Excuvator, Civil Engineer | ITCon | IT Consultant |  | A1100 | A1110 | SF | Not Started | Not Started | O and G | O and G | O and G.4 (New WBS)-3 | O and G.4 (New WBS)-3 | Trenching and Excavation | Pipe laying | 1 | R-12 | R-12 |  | 17280000 | 200000 | 17380000
A1110 | Not Started | O and G.4 | Pipe laying | 2025-03-19 08:00 | 2025-04-07 17:00 | Excuvator, Civil Engineer, Mechinacal Engineer | LiR | Roy Li |  | A1110 | A1120 | SF | Not Started | Not Started | O and G | O and G | O and G.4 (New WBS)-3 | O and G.4 (New WBS)-3 | Pipe laying | Walding and Coating | 0 | R-12 | R-13 |  | 120000 | 280000 | 128000
A1120 | Not Started | O and G.4 | Walding and Coating | 2025-04-08 08:00 | 2025-04-17 17:00 | Mechinacal Engineer, Weld Mechine | RiceB | Barbara Rice, PMO Director |  | A1120 | A1140 | FS | Not Started | Not Started | O and G | O and G | O and G.4 (New WBS)-3 | O and G.4 (New WBS)-3 | Walding and Coating | Valve installation | 0 | R-13 | R-15 |  | 4000000 | 544000 | 4001000
A1140 | Not Started | O and G.4 | Valve installation | 2025-04-18 08:00 | 2025-04-22 17:00 | Technician, Mechinacal Engineer | ChopraA | Amit Chopra |  | A1140 | A1150 | FS | Not Started | Not Started | O and G | O and G | O and G.4 (New WBS)-3 | O and G.4 (New WBS)-3 | Valve installation | backfalling and compaction | 0 | R-15 | R-12 |  | 80000 | 112000 | 82000
A1150 | Not Started | O and G.4 | backfalling and compaction | 2025-04-23 08:00 | 2025-04-30 17:00 | Civil Engineer, Excuvator | AbrahamM | Molly Abraham |  | A1150 | A1200 | FS | Not Started | Not Started | O and G | O and G | O and G.4 (New WBS)-3 | O and G.4 (New WBS)-3 | backfalling and compaction | Pipeline Marking | 0 | R-12 | R-15 |  | 960000 | 300000 | 990000
A1160 | Not Started | O and G.5 | Hydrostatic testing | 2025-05-05 08:00 | 2025-05-11 16:00 | Mechinacal Engineer, Testing Equipment | WrenJ | Jo Wren |  | A1200 | A1160 | FS | Not Started | Not Started | O and G | O and G | O and G.4 (New WBS)-3 | O and G.5 (New WBS)-4 | Pipeline Marking | Hydrostatic testing | 0 | R-15 | R-13 |  | 1680000 | 132000 | 1690000
A1170 | Not Started | O and G.5 | Electrical System installation | 2025-05-12 08:00 | 2025-05-16 17:00 | Electrical Engineer | ATM ENG | Automation Systems Engineer |  | A1160 | A1170 | FS | Not Started | Not Started | O and G | O and G | O and G.5 (New WBS)-4 | O and G.5 (New WBS)-4 | Hydrostatic testing | Electrical System installation | 0 | R-13 | R-14 |  | 560000 | 31800000 | 590000
A1180 | Not Started | O and G.5 | instrumation Calibration | 2025-05-17 08:00 | 2025-05-22 17:00 | Electrical Engineer, Technician | IT | Information Technology Group |  | A1170 | A1180 | FS | Not Started | Not Started | O and G | O and G | O and G.5 (New WBS)-4 | O and G.5 (New WBS)-4 | Electrical System installation | instrumation Calibration | 0 | R-14 | R-14 |  | 160000 | 14400000 | 190000
A1190 | Not Started | O and G.5 | Commessionation and Start up | 2025-05-23 08:00 | 2025-05-29 17:00 | Project Manager, Electrical Engineer | Product Dev | Product Development Resources |  | A1180 | A1190 | FS | Not Started | Not Started | O and G | O and G | O and G.5 (New WBS)-4 | O and G.5 (New WBS)-4 | instrumation Calibration | Commessionation and Start up | 0 | R-14 | R-11 |  | 512000 | 17280000 | 519000
A1200 | Not Started | O and G.4 | Pipeline Marking | 2025-05-01 08:00 | 2025-05-04 16:00 | Technician | ManufEng | Manufacturing Engineering Group | [16 empty] | 48000 | 120000 | 49000
[7 empty] | HillF | Frank Hill
[7 empty] | WestL | Larry West
[7 empty] | BaxterS | Sue Baxter
[7 empty] | WynnA | Alice Wynn
[7 empty] | ProductMktg | Product Marketing Group
[7 empty] | LincolnR | Robert Lincoln | Manufacturing Engineer
[7 empty] | ShawH | Harry Shaw | Senior Engineering Lead
[7 empty] | JacksonL | Lendell Jackson
[7 empty] | RickelsS | Sam Rickels
[7 empty] | IthanP | Peg Ithan
[7 empty] | Corporate | Corporate Resources
[7 empty] | Bpmpmo | Business Process PMO
[7 empty] | JohnsonR | Rea Johnson
[7 empty] | McneillL | Lori McNeil
[7 empty] | Operations | Process Operations
[7 empty] | BillingsJ | Judy Billings
[7 empty] | Chuf | Frank Chu
[7 empty] | Contr | External Contractors
[7 empty] | Bpm001 | BPM Consultant 1
[7 empty] | Bpm002 | BPM Consultant 2
[7 empty] | Bpm003 | BPM Consultant 3
[7 empty] | FrostB | Ben Frost
[7 empty] | CooperP | Peter Cooper
[7 empty] | PetersonM | Michelle Peterson
[7 empty] | PrescottW | Wayne Prescott
[7 empty] | E&C Resources | E&C Resources
[7 empty] | Subcontractors | Subcontractor
[7 empty] | Trades | Trades
[7 empty] | Management | Management
[7 empty] | Purchasing | Purchasing Department
[7 empty] | Engineering | Engineering Department
[7 empty] | Cretefinisher | Concrete Finisher
[7 empty] | Admin | Administrator
[7 empty] | Fabrication | Fabrication
[7 empty] | Elev Inst | Elevator Installer
[7 empty] | Elec | Electrician
[7 empty] | Floor | Floor and Carpet Layer
[7 empty] | Operator | Operator
[7 empty] | Plumb | Plumber
[7 empty] | FCarp | Finish Carpenter
[7 empty] | RCarp | Rough Carpenter
[7 empty] | GenLabor | Laborer-Construction
[7 empty] | FieldEng | Field Engineer
[7 empty] | IrnWrk | Ironworker
[7 empty] | FieldEngSnr | Field Eng-Senior
[7 empty] | FieldEngAsst | Field Eng-Assistant
[7 empty] | Exc | Excavator
[7 empty] | KimP | Paul Kim | Design Engineer
[7 empty] | YoungJ | Jeff Young | Analyst
[7 empty] | PMs | Project Managers
[7 empty] | ResnerW | Wendy Resner | Automation Systems Engineer
[7 empty] | DesEng | Design Engineer
[7 empty] | McGuireO | Owen McGuire, Project Manager
[7 empty] | Project Controls | Project Controls | Accounts Manager
[7 empty] | InsEng | Instrumentation Engineer
[7 empty] | HVAC | HVAC
[7 empty] | Millwork Carpentry | Millwork Subcontractor
[7 empty] | Thermal Protection | Thermal Protection Subcontractor
[7 empty] | Finishes | Finishes & Fit-out Subcontractor
[7 empty] | Concrete-Sub | Concrete Foundation Subcontractor
[7 empty] | Specialty Metals | Specialty Metal Fabricator Subcontractor
[7 empty] | Pools | Pool Installation Subcontractor
[7 empty] | Conveying-Sub | Conveying Subcontractor
[7 empty] | Fire Suppression | Fire Suppression Subcontractor
[7 empty] | Landscaping | Landscaping Subcontractor
[7 empty] | Specialties | FF&E Specialties
[7 empty] | Drywall | Drywall Subcontractor
[7 empty] | Roofing | Roofing Subcontractor
[7 empty] | Glass | Glass & Glazing Subcontractor
[7 empty] | Paving | Paving & Roadways Subcontractor
[7 empty] | Utilities | Utilities Subcontractor
[7 empty] | OPTGP | Operations Test Group
[7 empty] | INSP | Inspections | Senior Inspector
[7 empty] | Hydro | Hydroblaster
[7 empty] | Paint | Painter
[7 empty] | Material | Material Resources
[7 empty] | Test resource | New Resource Name
[7 empty] | Test Resource Child | New Resource Name-1
[7 empty] | R | Skill Age
[7 empty] | R-1 | Irfan Haider PM
[7 empty] | R-2 | Anwaar Site Engr
[7 empty] | R-3 | Dua Adviser
[7 empty] | R-4 | Shoaib COO
[7 empty] | R-5 | Cement
[7 empty] | R-6 | sand
[7 empty] | R-7 | Tractor
[7 empty] | R-8 | Mixer
[7 empty] | R-9 | Jaivd
[7 empty] | R-10 | Oil and Gas Project
[7 empty] | R-11 | Project Manager
[7 empty] | R-12 | Civil Engineer
[7 empty] | R-13 | Mechinacal Engineer
[7 empty] | R-14 | Electrical Engineer
[7 empty] | R-15 | Technician
[7 empty] | R-16 | Excuvator
[7 empty] | R-17 | Weld Mechine
[7 empty] | R-18 | Testing Equipment
[7 empty] | R-19 | Materials
[7 empty] | AC | Cost